## Test summary report
Tester: Nguyễn Trương Hoàng Thái 20127625, Trương Quốc Huân 20127172, Phan Thanh Thúy 20127350, Dương Đình Hiếu 20127675
Date: 08/12/2022
Number of functions were tested | Number of test cases | Number of passed test cases | Number of failed test cases of a function
5 | 24 | 17 | 6

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
UI01 | Cannot search (because user didn't log in) | 1. Visit the website 2. The system displays the website homepage 3. Click the search bar 4. Enter the video name you want to search or any related description information 5. Click the search icon 6. The system searches and gives the videos with the closest results to the information you need to find Expected Result (ER): The video you just searched for Actual Result: You cannot search because you are not logged in | U02 | High | Trương Quốc Huân 20127172 | 2022-08-11 | Open
UI05 | Some video can't be played | 1. Visit the website 2. Go to homepage display of the website 3. Clicks on a random video 4. The system plays the selected video Expected Result (ER): The video is played and user can view the content of selected video Actual Result: Some videos can not be played because it doesn't exist in local system | U01 | Low | Nguyễn Trương Hoàng Thái 20127625 | 2022-08-11 | Open
UI02 | User doesn't enter "Re-Password" section when sign up | 1. Visit the website 2. Go to homepage not login display of the website 3. Go to login and sign up pages 4. Input username password, email 5. Click button sign up 6. The system will alert notification succesful ER: Fail registration Actual Result: succesful registration | U03 | Low | Nguyễn Trương Hoàng Thái 20127625 | 2022-08-12 | Open
UI03 | User doesn't enter "Re-Password" and "Email" sections when sign up | 1. Visit the website 2. Go to homepage not login display of the website 3. Go to login and sign up pages 4. Input username password 5. Click button sign up 6. The system will alert notification succesful ER: Fail registration Actual Result: succesful registration | U03 | Low | Nguyễn Trương Hoàng Thái 20127625 | 2022-08-12 | Open
UI03 | Unable to respond to other comments | 1. Visit the website 2. Go to the homepage display of the website 3. Clicks on "Log in" button 4. Enter "test4" for username, "123456" for password 5. Click on any video 6. The system plays the selected video 7. Scroll down the comment list, select any comment and click "Reply" 8. Type in "Try comment feedback" 9. Click "Comment" for feedback Expected Result (ER): The system posts feedback comments below the main comment. Actual Result: You cannot comment | U10 | Low | Phan Thanh Thúy 20127350 | 2022-08-11 | Open
UI04 | The system does not report a login error | 1. Visit the website 2. Go to the homepage display of the website 3. Click on any video 4. The system plays the selected video 5. Scroll down the comment list, select any comment and click the like icon. Expected Result (ER): The system displays a message asking you to log in Actual Result: The message board has not been displayed because this function has not been programmed. | U10 | Low | Phan Thanh Thúy 20127350 | 2022-08-11 | Open | Because it is a detailed notification function to users, it is not required and does not affect other functions much.
UI05 | Can't like comment | 1. Visit the website 2. Go to the homepage display of the website 3. Clicks on the "Log in" button 4. Enter "test4" for username, "123456" for password 5. Click on any video 6. The system plays the selected video 7. Scroll down the comment list, select any comment and click the like icon 8. The system updates the number of likes and changes the color of the like icon. Expected Result (ER): Click like to get successful comments. See the number of likes of that comment. Actual Result: The system does not change state. | U10 | Low | Phan Thanh Thúy 20127350 | 2022-08-11 | Open